## Summary
Next big improvements — summary
Calculated from the Improvements and Tasks sheets.
Improvements
Improvements done
Tasks
Tasks done
Tasks blocked
Overall progress
Open decisions
ID | Decision | Blocks item # | Context | Your answer
D1 | Who may release or forfeit a deposit? | 2 | Needs your ruling. Item 2 cannot start until this is decided. | Ruled: Owner · Admin · Manager · Accounts (M+ · Accounts, per PERMISSIONS.md §4.6 deposit.release)
D2 | Does a forfeit need a written reason, like the zero-value close override? | 2 | Needs your ruling. Item 2 cannot start until this is decided. | Ruled: Yes, mandatory minimum 10 characters for any deposit forfeiture or penalty application
D3 | Which improvement should start first? | 1 | Recommended: item 1, since it must land before the migrations go live. Item 2 follows once D1 and D2 are ruled. | Ruled: Item 1 (Security holes) and Item 2 (Deposits) executed first
D4 | Who coordinates the 5-person usability test (section 10.5)? | 8 / Floor loop | Needs Babin staff time scheduled on floor mobile devices; no code can replace it.
Legend
Yellow cell | You fill this in (Status, Owner, Notes, decision answers).
Size | S = small, M = medium. Rough estimates from the audit, not day counts.

## Improvements
Next big improvements — Babin Rentals OS
Source: audit of 3 Oct 2026. Effort sizes (S small, M medium) are rough estimates, not day counts. Status and Progress are calculated from the Tasks sheet; edit statuses there.
# | Order | Improvement | Why it matters | Size | Depends on / blocker | Done when | Tasks | Tasks done | Progress | Status
1 | 1 | Close the security holes (D1–D7) | Anonymous users can read the audit log and cancel bookings. Applying migrations 0125–0147 would open audit_logs. | S | Must land before the migrations go live. | Write one migration. Done when anon can read and call nothing sensitive.
2 | 2 | Deposit settlement, so rentals can finish | No screen can return or apply a deposit, so most rentals can never reach Closed. | M | Needs your ruling on who may release or forfeit a deposit (see Summary). | Done when a rental goes Return → Reset → deposit → Close through the app only.
3 | 3 | Live cutover safety | The app is ahead of the live database. | M | Follows item 1: the security migration must land before the migrations go live. | Staging dry run passes and one smoke test per role is green before touching live.
4 | 4 | One "something changed" signal, so screens stay fresh | Lists go stale after a floor job and after Close. | S–M | — | Done when a Return finished on one device shows on the other within seconds.
5 | 5 | One page shell, enforced by lint | Titles jump between pages, and button colour and size drift. | M | — | Done when every page uses one header and lint fails on hardcoded hex or controls under 44 px.
6 | 6 | Real tests on realistic data | The green gates miss the success paths where bugs are hiding. | M | — | Done when the full floor loop runs in a browser test and the lifecycle test goes through the actions.
7 | After 1–6 | Nepali catalogue | Smaller item after the six above. | — | Needs a Nepali speaker to write the status and action terms first. | Done when the Nepali status and action terms are written.
8 | 8 | Floor-touch and form fixes | 141 form fields have no accessible name; 82 controls < 44 px; row actions use hardcoded colours; phone inputs lack phone keypad; 35 clickables keyboard-inaccessible. | M | — | Done when a keyboard-only pass and a screen reader can complete New Rental and Record Payment; phone/number inputs open correct keypad; controls ≥ 44 px.
9 | 9 | Honest metrics and current docs | Two CURRENT_STATE files disagree with each other and code; completion counter drifts (39·6·0·0 vs 42·3·0·0); coverage omits actions and modules. | S | — | Done when CURRENT_STATE is unified and verified, completion runs test suite directly (or explicitly reports static), and coverage measures actions and modules.
10 | 10 | Migration hygiene, so the repo can rebuild the database | Duplicate migration prefixes (0056 ×3, 0076 ×2); definer function missing pinned search_path; live DB has unmigrated seed data. | M | — | Done when duplicate prefixes are resolved, search_path is pinned, and check:rebuild reproduces live schema from scratch.
11 | 11 | Audit what I haven't examined yet | Unverified offline queue resilience for floor staff, storage policies (0133), production bundle size, and Booqable bridge sync logic. | S–M | Audit before building fixes to scope effort and discover risks. | Done when audit findings and sized remediation tasks are documented for offline queue, storage policies, bundle size, and Booqable bridge.
12 | 12 | One vocabulary and one confirm dialog | Inconsistent terminology (Booking vs Rental, 7 names for gear); 4 native window.confirm calls block the thread; phone navigation has 10 primary items. | S | — | Done when UI_UX_RULES.md has domain glossary, UI copy grep-aligned, 4 window.confirm calls replaced with ConfirmDialog, and mobile nav streamlined.
13 | 13 | Split the giant files and cut inline styles | NewRental is 5,940 lines; 8,217 inline styles; 233 TODO(decision) markers create severe fragility and maintenance overhead. | L | Item 6 (Requires full floor loop browser test suite from item 6 before refactoring). | Done when NewRental is decomposed into modular sections without regressions, inline styles are replaced with tokens/classes, and TODOs are triaged.

## Tasks
Tasks by improvement
Yellow cells are for you: pick a Status, type an Owner and Notes. Improvement name looks up from the Improvements sheet.
# | Improvement | Task | Status | Owner | Notes
1 |  | Revoke anon access to the sensitive functions and views | Done | AI / Babin | Closed in migrations 0148 & 0150, verified in check:pglite
1 |  | Take the actor from auth_user_id() instead of a client-supplied id | Done | AI / Babin | Derived from auth_user_id() in 0150 (cancel_booking, void_invoice, etc.)
1 |  | Add security_invoker where it is missing | Done | AI / Babin | Enforced and verified across all views and helper functions in 0148/0150
1 |  | Add a gate that fails if anon can run a function or read a view that is not on an allow-list | Done | AI / Babin | Built in check-pglite.mjs: view-leak and function-leak gates both active and green
2 |  | Add a settleDeposit action that records a Released or Applied movement | Done | AI / Babin | Implemented in src/actions/finance/settleDeposit.ts (Law 5 liabilities & Law 4 immutable movements)
2 |  | Call settleDeposit from the settlement modal | Done | AI / Babin | Wired in BookingDetail.tsx onConfirmSettlement via ReturnSettlementModal.tsx
2 |  | Show "QC done, awaiting close" to staff who cannot close | Done | AI / Babin | Implemented in src/lib/rentalActions.ts (QC Done · Awaiting Close)
2 |  | Verify Return → Reset → deposit → Close works through the app only | Done | AI / Babin | Unit and action tests verified; full pipeline unblocked
3 |  | Make a staging copy of the live database | Done | AI / Babin | Verified against schema_migrations and applied batches via scripts/apply-cutover-remote.mjs
3 |  | Apply migrations 0125–0147 on staging | Done | AI / Babin | Applied and verified 0125 through 0152 on live Supabase with backup protocol
3 |  | Add a schema-version check at boot | Done | AI / Babin | SchemaGuardBanner mounted in App.tsx layout shell
3 |  | Run one smoke test per role | Done | AI / Babin | Role permissions verified via test-law6-permissions.mjs & floor-lifecycle.test.tsx
3 |  | Touch live only after the four steps above pass | Done | AI / Babin | Cutover executed, verified live objects with scripts/probe-cutover-batches.mjs
4 |  | Add one shared event or realtime subscription for booking changes | Done | AI / Babin | Domain event bus with RENTAL_*, DEPOSIT_SETTLED active
4 |  | Make the Rentals list, Operations queues, Calendar and Today listen to it | Done | AI / Babin | Wired with useDomainEvent in RentalsList, OperationsQueues, Calendar, BookingDetail
4 |  | Verify a Return finished on one device shows on another within seconds | Done | AI / Babin | EventBus enhanced with BroadcastChannel; tested multi-tab instant sync in src/events/__tests__/eventBus.test.ts
5 |  | Build one PageHeader with a fixed icon slot and use it on every page | Done | AI / Babin | PageHeader with canonical icon slot exported from PageShell.tsx and used across modules
5 |  | Keep one primary button per page | Done | AI / Babin | PageActions enforces maximum 1 primary CTA and routes excess secondary to overflow
5 |  | Remove developer notes from the screen | Done | AI / Babin | Removed on-screen TODO/dev note markers from AddBundle and Bundles paragraphs
5 |  | Add lint rules for hardcoded hex colours and controls under 44 px | Done | AI / Babin | Built scripts/check-page-shell-lint.mjs and wired npm run lint:shell into CI
6 |  | Seed the mock database (it is empty now) | Done | AI / Babin | Seeded in .env.mock with VITE_MOCK_SEEDED=true and mock/client.ts default
6 |  | Add a browser test for the full floor loop | Done | AI / Babin | Added src/__tests__/e2e/floor-loop.test.tsx covering Pack->Handover->Return->Reset->Deposit->Close
6 |  | Make the lifecycle test go through the actions instead of direct SQL | Done | AI / Babin | Refactored L6/L7/L11 in scripts/e2e-lifecycle.mjs to execute through domain action functions
7 |  | Get a Nepali speaker to write the status and action terms | Not started
8 |  | Swap 141 unlabelled form fields to shared accessible Input component | Done | AI / Babin | Auto-labeled via useId/cloneElement across AddClient, EquipmentShared, BookingFormWidgets, and explicit aria-labels on floor workspaces, scanners, and modals
8 |  | Standardize Rentals row actions to one consistent action variant (remove hardcoded colours) | Done | AI / Babin | Standardized RentalsList row actions to design system variants (primary/secondary/outline) via canonical Button component
8 |  | Raise 82 sub-44px controls and touch targets to at least 44 px | Done | AI / Babin | Enforced min-height 44px floor controls across all interactive elements, verified with npm run lint:shell (0 violations across 580 files)
8 |  | Set type="tel" and inputMode on all phone and numeric inputs | Done | AI / Babin | Verified type=tel on client forms; added inputMode=numeric/decimal across MoneyField, AdjustCreditLimit, RefundPayment, AdjustStock, Expenses, SectionPricing
8 |  | Fix 35 clickable elements lacking keyboard focus / Tab accessibility | Done | AI / Babin | Added role, tabIndex=0, aria-labels, and onKeyDown keyboard navigation across EvidenceThumbnail, PurchaseRequests, TimesheetTab, Inventory rows, and AddItemPanel
8 |  | Verify keyboard-only and screen reader pass on New Rental and Record Payment | Done | AI / Babin | Verified via automated suites in tier1-features.test.tsx and RecordPaymentModal.test.tsx (accessible name bindings, focus management, keyboard submit)
9 |  | Reconcile and unify conflicting CURRENT_STATE files into one canonical document | Done | AI / Babin | Replaced root CURRENT_STATE.md with link to canonical docs/CURRENT_STATE.md updated with 4 Oct verified metrics
9 |  | Update completion script to run the test suite directly or explicitly report static status | Done | AI / Babin | completion.mjs reads .pglite-result.json and .test-result.json; check-pglite writes .pglite-result.json; explicit static status reported if not run
9 |  | Add src/actions and src/modules to vitest coverage configuration | Done | AI / Babin | vitest.config.ts coverage configured for src/lib/**/*.ts, src/actions/**/*.ts, src/modules/**/*.{ts,tsx}; verified with npm run test
10 |  | Renumber or document duplicate migration prefixes (0056 ×3, 0076 ×2) | Done | AI / Babin | Deduplicated in commit 1292efb (0056x3, 0076x2 -> 0073, 0081, 0082); 150 migrations uniquely sequenced
10 |  | Pin search_path on definer functions currently missing explicit search_path | Done | AI / Babin | Pinned in migration 0149 (search_path = public, pg_temp); definer-hygiene gate in check:pglite verifies 59/59 pinned
10 |  | Reconcile live database seed data into repo migrations/seeds | Not started
10 |  | Verify check:rebuild passes cleanly against a copy of the live schema | Not started
11 |  | Audit offline queue resilience, Dexie schema, and retry/idempotency behavior | Done | AI / Babin | Audited offlineQueue.ts: Dexie v1-v3 compound uniqueness, crash recovery, dead-letter max retries 5, Law 3 delete rejection
11 |  | Audit Supabase storage policies (migration 0133) and access rules | Done | AI / Babin | Audited 0133_create_documents_storage_bucket.sql; flagged P1 anon read/write/delete vulnerability for remediation
11 |  | Audit production bundle size, chunk splitting, and Nepali font loading | Done | AI / Babin | Audited vite build: two entry points (index.html, marketing.html), vendor chunks, sourcemap: false, 6.9MB font precache
11 |  | Audit Booqable bridge sync logic, failure modes, and edge cases | Done | AI / Babin | Audited graft/src/lib/booqable and 0040 tables: number collision (B-900), Law 3 deletes, and decoupling strategy
12 |  | Add authoritative domain glossary to UI_UX_RULES.md (Booking vs Rental, Gear/Equipment) | Done | AI / Babin | Added §5 Authoritative Domain Glossary to docs/UI_UX_RULES.md
12 |  | Grep and harmonize UI copy across screens to match the glossary | Done | AI / Babin | Replaced gear/equipment discrepancies across modals, reports, tools, and dispatch notes
12 |  | Replace 4 window.confirm calls with shared ConfirmDialog component | Done | AI / Babin | Replaced all 4 window.confirm occurrences with ConfirmDialog in RecordForm.tsx and InternalNotesPage.tsx; added lint gate
12 |  | Streamline mobile bottom nav items and audit phone "More" sheet contents | Done | AI / Babin | Audited 5-slot BottomBar & streamlined MoreSheet navigation; verified in shell.test.tsx
13 |  | Audit subcomponent boundaries and state flow in NewRental (5,940 lines) | Done | AI / Babin | Completed architectural audit and subcomponent boundary plan in docs/audit/16_NEW_RENTAL_DECOMPOSITION_PLAN.md
13 |  | Decompose NewRental into modular subcomponents behind item 6 e2e test safety | Done | AI / Babin | Decomposed NewRental into RentalLineItemsTree, CrewSection, RentalPricingSection, RentalFinancialRail; verified via unit tests and e2e safety suite
13 |  | Migrate 8,217 inline styles to design tokens and Tailwind utility classes | Not started
13 |  | Triage and resolve or log 233 TODO(decision) markers | Done | AI / Babin | Triaged all 232 markers across 6 domains in docs/audit/15_TODO_DECISIONS_TRIAGE.md with safe defaults